## Tabelle1
Todo	What	comment	Who	Status	Until
Git Repository	create it		Alex	done	23.03.15
Requirement software	Check if there are recommendations for requirement / Or Check out 2 of the provides list		Carmen	open	23.03.15
Use Cases 1	Multiuser System: create an account, login incl access control (admin, user, guest)		Daly	done	23.03.15
Use Cases 2	Admin: delete user, delete recipes, maintain provided ingredient list, ..	user cannot delete or change user data, admin has additional functions	Daly	done	23.03.15
Use Cases 3	Upload recipes with pictures	owner should be known and owner /admin can change recipe	Daly	done	23.03.15
Use Cases 4	Search for recipes by ingrediens and recipe names and view them (for guests as well), Download of recipes	ingredience should be structured	Alex	pending discussion	23.03.15
Use Cases 5	Favorite recipes, create lists of recipes	user can have more than 1 list	Alex	pending discussion	23.03.15
Use Cases 6	Create shoppling lists of one or more recipes	save shopping lists	Carmen	done	23.03.15
Use Cases 7	Create meal-plan		Carmen	done	23.03.15
Requirements
Technology	Java and Python – Serversite?		Alex	open	23.03.15
Technology	Clientside – GUI Vaadin?
Requirement	Requirement - data		Carmen	open	09.04.15
Requirement	Requirement – Interface (GUI) and Navigation		Alex	open	09.04.15
Requirement	Requirement – personal and transactional		Daly	open	09.04.15
Requirement	Non-functional: Guest is only allowed to search for recipes and view them, create a new account, nothing else. Remove other non-functional parts for that		Carmen	open	09.04.15